## Sitemap
Section | Page | Path | Task | Status | Priority | Owner | Notes | Updated
HOMEPAGE
Homepage | Home | / | The landing page (hero video, featured section, subscription cards, footer)
Homepage | Home | / | Top promo bar with welcome offer | Done | P1 high
Homepage | Home | / | Site nav with logo and wordmark | Done | P1 high
Homepage | Home | / | Hero with single looping video | Done | P1 high
Homepage | Home | / | Hero CTA button placed bottom right | Done | P1 high
Homepage | Home | / | Featured section with halo badge and trust line | Done | P1 high
Homepage | Home | / | Compose your formula button copy | Done | P2 medium
Homepage | Home | / | Subscription section with three cards | Done | P1 high
Homepage | Home | / | Footer that scales with the page | Done | P2 medium
Homepage | Home | / | Mobile menu (hamburger) | Done | P1 high
Homepage | Home | / | Layout scales to large external monitors | Done | P1 high
Homepage | Home | / | Real product photo for featured section | Blocked | P2 medium |  | Waiting on photography assets
CONSULTATION QUIZ
Consultation quiz | Quiz overview | /quiz | The quiz is a single page that walks the customer through 31 questions one at a time. Each question below shares the same URL but is tracked separately so we can polish each step.
Consultation quiz | Quiz overview | /quiz | Quiz framework working end to end | Done | P0 critical
Consultation quiz | Quiz overview | /quiz | Each question reachable by a step number in the URL | In progress | P2 medium |  | Refactoring quiz from single-page screen state to per-route pages (/quiz/q/[id]). Designers can deep-link any question.
Consultation quiz | Quiz overview | /quiz | Save partial answers if customer drops off | Todo | P2 medium
Consultation quiz | Quiz overview | /quiz | Polish quiz typography across all questions | Todo | P1 high |  | Headings and body text feel too small or mono on some steps
Consultation quiz | Quiz overview | /quiz | Mobile usability check on every question | Todo | P1 high
Consultation quiz | Step 1 of 31 | /quiz/q/1 | About You: How old are you?
Consultation quiz | Step 1 of 31 | /quiz/q/1 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 2 of 31 | /quiz/sex | About You: What is your biological sex?
Consultation quiz | Step 2 of 31 | /quiz/sex | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 3 of 31 | /quiz/q/3 | About You: Where do you live?
Consultation quiz | Step 3 of 31 | /quiz/q/3 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 4 of 31 | /quiz/q/4 | About You: How would you describe your environment?
Consultation quiz | Step 4 of 31 | /quiz/q/4 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 5 of 31 | /quiz/q/5 | About You: How much water do you drink daily?
Consultation quiz | Step 5 of 31 | /quiz/q/5 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 6 of 31 | /quiz/q/6 | About You: How many hours of sleep do you typically get?
Consultation quiz | Step 6 of 31 | /quiz/q/6 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 7 of 31 | /quiz/q/7 | About You: How would you rate your daily stress level?
Consultation quiz | Step 7 of 31 | /quiz/q/7 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 8 of 31 | /quiz/q/8 | About You: How would you describe your diet?
Consultation quiz | Step 8 of 31 | /quiz/q/8 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 9 of 31 | /quiz/q/9 | About You: How much daily sun exposure do you get?
Consultation quiz | Step 9 of 31 | /quiz/q/9 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 10 of 31 | /quiz/q/10 | About You: Are you currently pregnant or breastfeeding?
Consultation quiz | Step 10 of 31 | /quiz/q/10 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 11 of 31 | /quiz/q/11 | Your Skin: How would you describe your skin type?
Consultation quiz | Step 11 of 31 | /quiz/q/11 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 12 of 31 | /quiz/q/12 | Your Skin: What are your biggest skin concerns right now?
Consultation quiz | Step 12 of 31 | /quiz/q/12 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 13 of 31 | /quiz/q/13 | Your Skin: How sensitive is your skin to the sun?
Consultation quiz | Step 13 of 31 | /quiz/q/13 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 14 of 31 | /quiz/q/14 | Your Skin: How does your skin feel after cleansing with just water?
Consultation quiz | Step 14 of 31 | /quiz/q/14 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 15 of 31 | /quiz/q/15 | Your Skin: How often do you experience breakouts?
Consultation quiz | Step 15 of 31 | /quiz/q/15 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 16 of 31 | /quiz/q/16 | Your Skin: Do you experience any of the following?
Consultation quiz | Step 16 of 31 | /quiz/q/16 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 17 of 31 | /quiz/q/17 | Your Skin: How visible are your pores?
Consultation quiz | Step 17 of 31 | /quiz/q/17 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 18 of 31 | /quiz/q/18 | Your Skin: How would you describe your skin tone?
Consultation quiz | Step 18 of 31 | /quiz/q/18 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 19 of 31 | /quiz/q/19 | Your Skin: Rate the following about your skin right now.
Consultation quiz | Step 19 of 31 | /quiz/q/19 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 20 of 31 | /quiz/q/20 | Your Skin: Have you ever had an allergic reaction to a skincare product?
Consultation quiz | Step 20 of 31 | /quiz/q/20 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 21 of 31 | /quiz/q/21 | Routine and Preferences: How many steps is your current skincare routine?
Consultation quiz | Step 21 of 31 | /quiz/q/21 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 22 of 31 | /quiz/q/22 | Routine and Preferences: What texture do you prefer in a moisturiser?
Consultation quiz | Step 22 of 31 | /quiz/q/22 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 23 of 31 | /quiz/q/23 | Routine and Preferences: What type of cleanser do you prefer?
Consultation quiz | Step 23 of 31 | /quiz/q/23 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 24 of 31 | /quiz/q/24 | Routine and Preferences: Rank these skincare priorities from most to least important.
Consultation quiz | Step 24 of 31 | /quiz/q/24 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 25 of 31 | /quiz/q/25 | Routine and Preferences: Which ingredient philosophies matter to you?
Consultation quiz | Step 25 of 31 | /quiz/q/25 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 26 of 31 | /quiz/q/26 | Routine and Preferences: How adventurous are you with skincare ingredients?
Consultation quiz | Step 26 of 31 | /quiz/q/26 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 27 of 31 | /quiz/q/27 | Routine and Preferences: Have you used retinol or retinoids before?
Consultation quiz | Step 27 of 31 | /quiz/q/27 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 28 of 31 | /quiz/q/28 | Routine and Preferences: How much time do you spend on your skincare routine?
Consultation quiz | Step 28 of 31 | /quiz/q/28 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 29 of 31 | /quiz/q/29 | Routine and Preferences: Is there anything you would like to avoid in your products?
Consultation quiz | Step 29 of 31 | /quiz/q/29 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 30 of 31 | /quiz/q/30 | Routine and Preferences: Do you have any known skin allergies?
Consultation quiz | Step 30 of 31 | /quiz/q/30 | Design and copy polish for this step | Todo | P2 medium
Consultation quiz | Step 31 of 31 | /quiz/q/31 | Routine and Preferences: Would you like fragrance in your products?
Consultation quiz | Step 31 of 31 | /quiz/q/31 | Design and copy polish for this step | Todo | P2 medium
AFTER THE QUIZ
After the quiz | Results | /results | The page that shows the customer their personalised products and the regimen we recommend
After the quiz | Results | /results | Trust line near the top | Done | P2 medium
After the quiz | Results | /results | Ingredient cards expand when clicked to show details | Done | P1 high
After the quiz | Results | /results | 3D botanical scene shows alongside the recommendation | Done | P2 medium
After the quiz | Results | /results | Subscription plan picker is side by side | Done | P1 high
After the quiz | Results | /results | Mobile usability check | Todo | P1 high
After the quiz | Results | /results | Empty state and error state designs | Todo | P2 medium
After the quiz | Skin Analysis | /analysis | A breakdown of the customer's skin profile from their quiz answers
After the quiz | Skin Analysis | /analysis | Show the profile information clearly | Done | P1 high
After the quiz | Skin Analysis | /analysis | Visual breakdown of concerns and priorities | Todo | P1 high
After the quiz | Skin Analysis | /analysis | Compare with their previous quiz if they retake it | Todo | P3 low
After the quiz | Detailed Report | /report | A longer page that explains the customer's regimen in depth
After the quiz | Detailed Report | /report | Explain the rationale behind each product | Done | P1 high
After the quiz | Detailed Report | /report | Make it look right when printed | Todo | P2 medium
After the quiz | Detailed Report | /report | Add a download as PDF option | Todo | P3 low
CART AND CHECKOUT
Cart and checkout | Cart | /cart | The customer's bag and where they pick their subscription plan
Cart and checkout | Cart | /cart | Three subscription plan cards side by side | Done | P0 critical
Cart and checkout | Cart | /cart | Bi-monthly plan selected by default with 'Most Popular' tag | Done | P0 critical
Cart and checkout | Cart | /cart | Reassurance copy inside each plan card | Done | P1 high
Cart and checkout | Cart | /cart | Trust strip under the checkout button | Done | P1 high
Cart and checkout | Cart | /cart | Card colours follow the palette | Done | P2 medium
Cart and checkout | Cart | /cart | Empty cart screen invites them to start the quiz | Done | P2 medium
Cart and checkout | Cart | /cart | Stacks to one column on mobile | Done | P1 high
Cart and checkout | Cart | /cart | Routine summary panel with name, skin type, concerns, fragrance | Done | P1 high
Cart and checkout | Cart | /cart | Numbered routine steps (Cleanser → Serum → Moisturizer) | Done | P1 high
Cart and checkout | Cart | /cart | Per-item 'Selected for {concerns}' microcopy from the matching engine | Done | P1 high
Cart and checkout | Cart | /cart | Subscription nudge banner with one-tap switch to bi-monthly | Done | P0 critical
Cart and checkout | Cart | /cart | Per-plan inline price with savings chip and strikethrough anchor | Done | P1 high
Cart and checkout | Cart | /cart | Ship-to country selector with grouped region dropdown | Done | P0 critical
Cart and checkout | Cart | /cart | Multi-currency pricing (EUR / GBP / USD) repriced live on country change | Done | P0 critical
Cart and checkout | Cart | /cart | 'Edit responses' link returns to results to adjust the formula | Done | P2 medium
Cart and checkout | Checkout | /checkout | The handoff to Stripe where the customer enters card details
Cart and checkout | Checkout | /checkout | Hand off to Stripe for payment | Done | P0 critical
Cart and checkout | Checkout | /checkout | Trust strip under the pay button | Done | P1 high
Cart and checkout | Checkout | /checkout | Buttons follow the palette | Done | P2 medium
Cart and checkout | Checkout | /checkout | Recurring charge note for subscription plans | Done | P2 medium
Cart and checkout | Checkout | /checkout | Error message styling when payment fails | Todo | P2 medium
Cart and checkout | Checkout | /checkout | Currency-aware totals match the chosen ship-to country | Done | P0 critical
Cart and checkout | Confirmation | /confirmation | The thank you page after a successful payment
Cart and checkout | Confirmation | /confirmation | Verify the Stripe session and confirm the order | Done | P0 critical
Cart and checkout | Confirmation | /confirmation | Auto-create the order in our system after payment | Done | P0 critical
Cart and checkout | Confirmation | /confirmation | Show order details and next steps | Todo | P1 high
Cart and checkout | Confirmation | /confirmation | Show tracking link once the courier integration is live | Todo | P1 high
Cart and checkout | Confirmation | /confirmation | Currency symbol comes from Stripe session, not hardcoded | Done | P1 high
CUSTOMER ACCOUNT
Customer account | Account dashboard | /account | Where the customer manages their orders, subscription, and profile
Customer account | Account dashboard | /account | Sign in works end to end | Done | P0 critical
Customer account | Account dashboard | /account | Dashboard layout looks right | Done | P1 high
Customer account | Account dashboard | /account | Past orders view | Todo | P1 high
Customer account | Account dashboard | /account | Subscription management (pause, cancel, change plan) | Todo | P0 critical
Customer account | Account dashboard | /account | Retake the quiz from inside the account | Todo | P2 medium
Customer account | Account dashboard | /account | Edit profile and shipping address | Todo | P1 high
Customer account | Account dashboard | /account | 'Manage payment & billing' button → opens Stripe Customer Portal | Todo | P0 critical |  | Customer Portal handles add/remove/update cards, invoices, subscription pause/cancel, failed-payment recovery.
REFERENCE PAGES
Reference pages | Ingredients | /ingredients | A glossary of all the botanicals we use
Reference pages | Ingredients | /ingredients | Show every ingredient from the database | Done | P1 high
Reference pages | Ingredients | /ingredients | Filter by function or type | Todo | P2 medium
Reference pages | Ingredients | /ingredients | Detail page per ingredient (origin, function, scientific name) | Todo | P2 medium
Reference pages | Ingredients | /ingredients | Type and layout polish | Todo | P1 high
ADMIN TOOLS
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | The operations dashboard for picking, packing, printing labels, and exporting product data
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Only admins can sign in | Done | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | List of pending and fulfilled orders with filters | Done | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Assign barcodes when an order is fulfilled | Done | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Print one or all labels at once | Done | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Barcodes printed at GS1 standard size | Done | P1 high
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Download an XML file per product for INCI Beauty | Done | P1 high
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Cancel an order or delete a test order | Done | P2 medium
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Create a shipment with the Direx courier | Todo | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Close the daily manifest and schedule a pickup | Todo | P0 critical
Admin tools | Fulfillment Studio | fulfillment-studio (separate dashboard) | Auto deploy this dashboard when we push (currently manual) | Todo | P2 medium
Admin tools | Barcode Studio | barcode-studio (separate dashboard) | Where we manage our pool of product barcodes
Admin tools | Barcode Studio | barcode-studio (separate dashboard) | Manage which company prefix we issue from | Done | P0 critical
Admin tools | Barcode Studio | barcode-studio (separate dashboard) | Bulk import barcodes from an Excel file | Done | P0 critical
Admin tools | Barcode Studio | barcode-studio (separate dashboard) | Live preview at the actual print size | Done | P1 high
OUTSIDE SERVICES WE CONNECT TO
Outside services we connect to | Stripe (payments) | — | How we charge customers and run subscriptions
Outside services we connect to | Stripe (payments) | — | Send the customer to Stripe to pay | Done | P0 critical
Outside services we connect to | Stripe (payments) | — | Automatically create the order when Stripe confirms payment | Done | P0 critical
Outside services we connect to | Stripe (payments) | — | Subscription billing (bi-monthly and annual) | Done | P0 critical
Outside services we connect to | Stripe (payments) | — | Plan for what happens when a recurring charge fails | Todo | P1 high
Outside services we connect to | Stripe (payments) | — | Multi-currency Checkout Session (EUR / GBP / USD) | Done | P0 critical
Outside services we connect to | Stripe (payments) | — | Expanded allowed_countries to all Phase-1 shipping regions | Done | P1 high
Outside services we connect to | Stripe (payments) | — | Enable country-specific payment methods in Stripe Dashboard (iDEAL, Bancontact, SEPA, BACS, ACH, Apple/Google Pay, Klarna, Link) | Todo | P0 critical |  | Code path is ready — Stripe auto-displays methods when payment_method_types is omitted. Just needs dashboard enablement.
Outside services we connect to | Stripe (payments) | — | Stripe Customer Portal for saved payment methods + invoices + subscription pause | Todo | P1 high |  | Requires stripe_customer_id column on customers and a /api/billing-portal-session route.
Outside services we connect to | Stripe (payments) | — | Save stripe_customer_id from checkout.session.completed webhook | Todo | P1 high
Outside services we connect to | Supabase (database and storage) | — | Where customer data, products, and images live
Outside services we connect to | Supabase (database and storage) | — | Products and ingredients data set up | Done | P0 critical
Outside services we connect to | Supabase (database and storage) | — | Customer orders and quiz results data set up | Done | P0 critical
Outside services we connect to | Supabase (database and storage) | — | Barcode pool and product records data set up | Done | P0 critical
Outside services we connect to | Supabase (database and storage) | — | Admin role check so only the right people can use the dashboard | Done | P0 critical
Outside services we connect to | Supabase (database and storage) | — | Public product image storage (the bucket called products) | Done | P1 high
Outside services we connect to | Supabase (database and storage) | — | Upload one real product photo per barcode | Todo | P1 high
Outside services we connect to | INCI Beauty (product import) | — | External cosmetic ingredient database where our products get listed
Outside services we connect to | INCI Beauty (product import) | — | Generate the XML file from each product | Done | P1 high
Outside services we connect to | INCI Beauty (product import) | — | Download button inside the fulfillment dashboard | Done | P1 high
Outside services we connect to | INCI Beauty (product import) | — | Placeholder image hosted publicly | Done | P1 high
Outside services we connect to | INCI Beauty (product import) | — | Use a different image per product | Todo | P1 high
Outside services we connect to | INCI Beauty (product import) | — | Try a real import on INCI Beauty and confirm it works | In progress | P0 critical |  | First two imports rejected — invalid INCI ingredient names, wrong <info> usage, image mismatch. INCI Beauty deployed a fix for the image-ignored bug on their side. Test XML drafted for BOV to re-test the upload pipeline.
Outside services we connect to | INCI Beauty (product import) | — | Fix <info> field — emit self-closing instead of stuffing net_content | Todo | P1 high
Outside services we connect to | INCI Beauty (product import) | — | Per-product images served from /products/{gtin}.jpg with placeholder fallback | Todo | P1 high
Outside services we connect to | INCI Beauty (product import) | — | ingredients.inci_name column + COSING-validated names for every ingredient | Todo | P0 critical |  | Blocker for INCI Beauty acceptance — current ingredient names ('pH adjuster', 'Emulgade 1000 NI') are functional descriptors, not INCI.
Outside services we connect to | INCI Beauty (product import) | — | Update GS1 Verified portal entry for each GTIN we submit | Todo | P1 high |  | Operational — not technical. Ensures GS1 registry matches what we ship to INCI.
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | The courier that picks up parcels from our warehouse and delivers them
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Get our login working with their system | Todo | P0 critical
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Register the warehouse as a sender on their portal | Todo | P0 critical |  | Operational, not technical
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Confirm whether we ship Bulgaria only, or international too | Todo | P1 high
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Add a Create Shipment button per order with label download | Todo | P0 critical
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Close manifest and schedule pickup actions | Todo | P0 critical
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Automatic tracking updates every 6 hours | Todo | P1 high
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Customer can see tracking from their account | Todo | P1 high
Outside services we connect to | Direx Courier (Bulgarian shipping) | — | Shipped email with tracking link | Todo | P2 medium
DESIGN SYSTEM
Design system | Design Lab (open with ?lab=1) | — | The floating dev panel for trying different fonts, palettes, and card styles live on the page
Design system | Design Lab (open with ?lab=1) | — | Five font slots (headlines, inner pages, body, inner body, captions and buttons) | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Roughly 70 fonts to choose from | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Picker mode: click any text to see what controls it | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Per element override panel with bold, italic, underline, colour | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Six built-in design directions plus your own saved ones | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Six brand inspired directions (Aesop, Le Labo, Glossier, etc.) | Done | P2 medium
Design system | Design Lab (open with ?lab=1) | — | Seven built-in palettes plus your own hex picker | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Card corner style picker | Done | P2 medium
Design system | Design Lab (open with ?lab=1) | — | Modular palette: card surface, button background and text, borders, accents | Done | P1 high
Design system | Design Lab (open with ?lab=1) | — | Each section can collapse or expand | Done | P2 medium
Design system | Design Lab (open with ?lab=1) | — | Sitemap tab inside the panel (still there for quick navigation) | Done | P3 low
Design system | Design tokens | — | The shared colour and font variables that the whole site reads from
Design system | Design tokens | — | Font tokens applied across the site | Done | P1 high
Design system | Design tokens | — | Palette tokens (background, card, ink, button, line, accents) | Done | P1 high
Design system | Design tokens | — | Card radius token | Done | P2 medium
Design system | Design tokens | — | Refactor all old hardcoded fonts to use the tokens | Done | P1 high
Design system | Design tokens | — | Refactor inner pages (quiz, account) to use the same card token | Todo | P2 medium
OTHER THINGS TO DO
Other things to do | Brand identity | — | Logo, favicon, brand voice
Other things to do | Brand identity | — | Final logo design (currently using the rusalka illustration) | In progress | P0 critical
Other things to do | Brand identity | — | Favicon that matches the brand | Todo | P2 medium
Other things to do | Brand identity | — | Preview image used when sharing on social media | Todo | P2 medium
Other things to do | Brand identity | — | Written guide for brand voice and tone | Todo | P2 medium
Other things to do | Accessibility | — | Making the site usable by people with disabilities
Other things to do | Accessibility | — | Check colour contrast on every palette | Todo | P1 high
Other things to do | Accessibility | — | Make the quiz fully navigable with the keyboard | Todo | P1 high
Other things to do | Accessibility | — | Make the results page work for screen readers | Todo | P1 high
Other things to do | Accessibility | — | Make sure every clickable thing shows a focus ring | Todo | P1 high
Other things to do | Speed and performance | — | Making the site fast to load
Other things to do | Speed and performance | — | Hero video set up to load quickly | Done | P1 high
Other things to do | Speed and performance | — | Re-encode hero video to a smaller modern format | Todo | P2 medium
Other things to do | Speed and performance | — | Use Next.js optimised image component for product photos | Todo | P1 high
Other things to do | Speed and performance | — | Load only the font weights we actually use | Todo | P2 medium
Other things to do | Speed and performance | — | Run a Google speed test and fix the worst issues | Todo | P1 high